## Checklist
Diplomski plan: Checklist (dataset registry + pipeline + baseline)
Ukupno zadataka | 55 | Zavrseno | 21 | % Zavrseno | 38.18% | Blokirano | 3 | U toku | 1
ID | Faza | Naziv zadatka | Deliverable / opis | Alat | Start | Target | Status | % | Prioritet | Napomene | Link/Path
1 | F0 | Definisi cilj rada (1 pasus) | 1 pasus: šta gradiš + zašto (DE fokus) |  |  |  | Done | 100%
2 | F0 | Definisi kriterijum 'gotovo' (DoD) | Lista deliverable-a: registry, pipeline, reporti, baseline, prezentacija |  |  |  | Done | 100%
3 | F0 | Izaberi opseg dataset-a | Da li radiš sva 4 ili 2+1 (preporuka: 2 image + 1 tabular) |  |  |  | Done | 100% |  | Radim sva 4
4 | F0 | Postavi repo i strukturu foldera | docs/, src/, data/raw, data/curated, reports/, models/, infra/ | Git |  |  | Done | 100% |  | https://github.com/Milki19/cancer-platform.git
5 | F1 | Preuzmi SipakMed (cervical) | Download + smesti u data/raw/sipakmed | Kaggle |  |  | Done | 100%
6 | F1 | Preuzmi LC25000 (lung+colon) | Download + smesti u data/raw/lc25000 | Kaggle |  |  | Done | 100%
7 | F1 | Preuzmi rm1000 lung histo | Download + smesti u data/raw/rm1000 | Kaggle |  |  | Done | 100%
8 | F1 | Preuzmi thyroid recurrence (tabular) | Download + smesti u data/raw/thyroid | Kaggle |  |  | Done | 100%
9 | F1 | Licensing/napomene za citiranje | Zapiši licence i kako citiraš dataset u radu |  |  |  | Not Started | 0%
10 | F2 | Image profiling modul | Broj slika, klase, rezolucije, veličine fajlova | Python |  |  | Done | 100%
11 | F2 | Tabular profiling modul | Tipovi kolona, missing, distribucije, imbalance | Python |  |  | Done | 100%
12 | F2 | Detekcija duplikata (hash) | Exact duplicates (sha256) + izveštaj | Python |  |  | Not Started | 0%
13 | F2 | Near-duplicate detekcija (bonus) | Perceptual hash (pHash/aHash) za slike | Python |  |  | Not Started | 0%
14 | F2 | QC: blur/brightness outliers | Flag za mutne/previše tamne svetle slike | Python |  |  | Not Started | 0%
15 | F2 | Generiši početne profile reporte | reports/profile_<dataset>.html/pdf |  |  |  | Done | 100%
16 | F3 | Odluči registry: YAML ili Postgres | Preporuka: YAML MVP, posle Postgres |  |  |  | Not Started | 0%
17 | F3 | Definiši standard metadata schema | Minimalni skup polja + tipovi |  |  |  | Done | 100%
18 | F3 | Definiši pipeline steps | ingest, profile, qc, curate, train_baseline, serve |  |  |  | Done | 100%
19 | F3 | Nacrtaj arhitekturu | Dijagram: komponente + tok podataka | Draw.io |  |  | Not Started | 0%
20 | F3 | Definiši naming/versioning | Dataset version (v1, v2), run_id, manifest |  |  |  | Not Started | 0%
21 | F4 | CLI/komande skeleton | run, profile, curate, train, serve | Python |  |  | Not Started | 0%
22 | F4 | Registry implementacija | register/list/get, validacija unosa | Python |  |  | Not Started | 0%
23 | F4 | Ingestion modul | Kopiranje u standard strukturu + manifest + checksum | Python |  |  | Not Started | 0%
24 | F4 | Profiling integracija | Pipeline step: profile + upis rezultata | Python |  |  | In Progress | 50%
25 | F4 | QC step | Rule engine + flagged samples + summary | Python |  |  | Not Started | 0%
26 | F4 | Curation (images) | Resize/normalize + split (stratified) | Python |  |  | Done | 100%
27 | F4 | Curation (tabular) | Cleaning + encoding + split | Python |  |  | Done | 100%
28 | F4 | Baseline train (images) | Transfer learning baseline + log metrika | PyTorch/TF |  |  | Done | 100%
29 | F4 | Baseline train (tabular) | LogReg + XGBoost/LightGBM baseline | sklearn |  |  | Done | 100%
30 | F4 | Artifacts & folder conventions | models/, reports/, runs/<run_id>/... |  |  |  | Not Started | 0%
31 | F5 | Idempotency | Re-run ne duplira artefakte; koristi manifest/hash |  |  |  | Not Started | 0%
32 | F5 | Error handling + retry | Fail-safe: partial runs i clean recovery |  |  |  | Not Started | 0%
33 | F5 | Logging | Strukturisani logovi po step-u + run_id |  |  |  | Done | 100%
34 | F5 | Metrics | Trajanje koraka, broj fajlova, fail rate |  |  |  | Done | 100%
35 | F5 | Dataset catalog (mini) | Tabela/JSON index: šta imaš i gde |  |  |  | Not Started | 0%
36 | F5b | Kafka topics dizajn | dataset.registered, profile.completed, run.failed | Kafka |  |  | Blocked | 0%
37 | F5b | Producer/consumer prototip | Bar 2 servisa preko topic-a | Kafka |  |  | Blocked | 0%
38 | F5b | DLQ topic | Neuspešni događaji idu u *.dlq | Kafka |  |  | Blocked | 0%
39 | F6 | Eksperiment A: baseline bez QC | Treniraj i sačuvaj metrike |  |  |  | Not Started | 0%
40 | F6 | Eksperiment B: baseline sa QC | Ukloni flagged uzorke pa treniraj |  |  |  | Not Started | 0%
41 | F6 | Eksperiment C: split strategija | Uporedi random vs stratified |  |  |  | Not Started | 0%
42 | F6 | Sumarni report | Jedna tabela + grafici poređenja |  |  |  | Done | 100%
43 | F7 | Napraviti skeleton rada | Poglavlja + podnaslovi u Word-u | Word |  |  | Not Started | 0%
44 | F7 | Uvod + motivacija | 1-2 strane | Word |  |  | Done | 100%
45 | F7 | Dataset opis + EDA nalazi | 2-4 strane + tabele | Word |  |  | Not Started | 0%
46 | F7 | Dizajn sistema | Arhitektura + odluke | Word |  |  | Not Started | 0%
47 | F7 | Implementacija | Kako radi pipeline, strukture podataka | Word |  |  | Not Started | 0%
48 | F7 | Rezultati eksperimenata | Grafici + interpretacija | Word |  |  | Not Started | 0%
49 | F7 | Zaključak + future work | 1-2 strane | Word |  |  | Not Started | 0%
50 | F7 | Literatura i citati | Dataset citation + alati | Word |  |  | Not Started | 0%
51 | F8 | Outline slajdova | 10-12 slajdova plan | PPT |  |  | Not Started | 0%
52 | F8 | Nacrtaj arhitekturu (slajd) | Jedan glavni dijagram | PPT |  |  | Not Started | 0%
53 | F8 | Rezultati (slajdovi) | QC vs no-QC, performanse | PPT |  |  | Not Started | 0%
54 | F8 | Speaker notes | Kratke beleške šta govoriš | PPT |  |  | Not Started | 0%
55 | F8 | Proba odbrane | 10-12 min + pitanja |  |  |  | Not Started | 0%

## How to use
Kako da koristis ovaj checklist
1) Popuni Start/Target datume po zadacima koji su ti aktivni.
2) Status menjaj kroz padajuci meni: Not Started / In Progress / Blocked / Done.
3) % se racuna automatski iz Status-a (Done=100%, In Progress=50%).
4) Prioritet je opcion: Low/Medium/High.
5) Napomene i Link/Path: stavi putanju do reporta, commita, slajdova, itd.
Saveti
- Ne menjaj data/raw. Sve transformacije idu u data/curated/<dataset>/<version>.
- Nakon svake faze upisi kratak tekst u Word (1-2 strane) da ne gomilas.